## Instructions
Timeline Generator Format
Column A: Date the activity is scheduled for completion.
Column B: Anticipated days to complete each activity. Edit these numbers as needed to reflect the time needed at each stage.
Column C: Recruiting activity or stage.
Column D: Purpose of recruiting activity or stage - Alignment, Collaboration, Coordination + Planning, Outreach + Candidate Engagement, Shared Decision-Making
Column E: Who is involved and/or responsible for each activity or stage.
Instructions for Use
(Forward): Enter the date that you initiate this process in Box A5. Dates will automatically populate for all corresponding stages. Add or delete rows in the Candidate Review and Engagement section based on number of interview rounds.If at any point a step of the process is accelerated or delayed, simply type the date the task is completed in column and all tasks following will automatically update.
(Backward): Enter the date that you hope to have someone in the role by in Box A42 . Dates will automatically populate for all corresponding stages. Add or delete rows in the Candidate Review and Engagement section based on number of interview rounds.If at any point a step of the process is accelerated or delayed, simply type the date the task is completed in column and all tasks following will automatically update.
*Please note - these dates are populated without weekends/business days in mind and so will need to be adjusted accordingly.

## Recruiting Schedule (Forward)
Date | Time to Complete (In Days) | Activity | Purpose | Who's Involved/Responsible
Pre-Recruitment
2025-02-01 |  | Start CLI Process
2025-02-04 | 3 | Review CLI Resources. Conduct Council Readiness Assessment. | Planning + Coordination | Hiring Team
2025-02-07 | 3 | Draft job description. Reference 02_Building an Inclusive Job Description CLI resource. Templates available for program, fundraising/development, community engagement and ED recruitments on the Council Portal. | Alignment | Hiring Team
2025-02-10 | 1 | Establish hiring team. Engage hiring team and existing staff members for feedback on the job description. | Shared Decision-Making, Collaboration, Aligment | Hiring Team
2025-02-11 | 1 | Update position description based hiring team dicussion | Alignment | Hiring Team Lead
2025-02-12 | 1 | Complete CLI Submission Form to submit the role for publishing. | Planning + Coordination | Hiring Team Lead
|  | Posting | Recruitment
2025-02-13 | 5 | Position is posted on Bamboo HR and HQ outlets | Outreach + Candidate Engagement | HQ
|  | Post positions within local and regional outlets. See 04_Hiring Social Media Resources for customizable social media templates. | Outreach + Candidate Engagement | Hiring Team Lead
|  | While position is open, determine interview questions/prompts for first, second and (if applicable) third interviews. See 01_Collaborative Hiring Guide for ideas on how to creatively engage current staff in this stage of the process. | Planning + Coordination, Collaboration, Alignment | Hiring Team
| 14 | Position remains open. Average is about two weeeks, but adjust days in B15 as needed. | Outreach + Candidate Engagement | HQ
2025-02-27 |  | Position Closes |  | HQ
|  | Candidate Review and Engagement | Recruitment/Discernment
Round 1
2025-03-04 | 5 | Hiring team members conduct initial review of candidates | Discernment | Hiring Team
2025-03-09 | 1 | Hiring team selects candidates for first round interviews. | Shared Decision-Making, Collaboration, Aligment | Hiring Team
2025-03-10 | 3 | Invitations to first round interviews are sent. | Planning + Coordination, Outreach + Candidate Engagement | Hiring Lead
2025-03-13 | 7 | First round interviews begin | Outreach + Candidate Engagement | Hiring Team
2025-03-20 |  | First round interviews conclude. | Outreach + Candidate Engagement | Hiring Team
Round 2
2025-03-22 | 2 | Hiring team members conduct review of interview notes. | Discernment | Hiring Team
2025-03-23 | 1 | Hiring team selects candidates for second round interviews. | Shared Decision-Making, Collaboration, Aligment | Hiring Team
2025-03-24 | 1 | Invitations to second round interviews are sent. | Planning + Coordination, Outreach + Candidate Engagement | Hiring Lead
2025-03-27 | 3 | Second round interviews begin. | Outreach + Candidate Engagement | Hiring Team
2025-04-03 | 7 | Second round interviews conclude. | Outreach + Candidate Engagement | Hiring Team
Round 3
2025-04-05 | 2 | Hiring team members conduct review of interview notes. | Discernment | Hiring Team
2025-04-06 | 1 | Hiring team selects candidates for final interviews. | Shared Decision-Making, Collaboration, Aligment | Hiring Team
2025-04-07 | 1 | Final interview invitations are sent. | Planning + Coordination, Outreach + Candidate Engagement | Hiring Lead
2025-04-10 | 3 | Final interviews begin. | Outreach + Candidate Engagement | Hiring Team
2025-04-13 | 3 | Final interviews conclude. | Outreach + Candidate Engagement | Hiring Team
2025-04-14 | 1 | Hiring team meets to discuss and identify chosen candidate. | Shared Decision-Making, Collaboration, Aligment | Hiring Team
2025-04-15 | 1 | Offer is drafted and extended. | Shared Decision-Making, Collaboration, Aligment | Hiring Lead
|  | Offer Acceptance & Onboarding | Recruitment/Discernment
| TBD | Offer is accepted! Start date is identified.
Formulas:
Date = [Date, row above]+[Time to Complete (In Days)]
Date = [Date, row above]+[Time to Complete (In Days), row above]

## Recruiting Schedule (Backward)
Date | Time to Complete (In Days) | Activity | Purpose | Who's Involved/Responsible
Pre-Recruitment
2024-11-01 |  | Start CLI Process
2024-11-04 | 3 | Review CLI Resources. Conduct Council Readiness Assessment. | Planning + Coordination | Hiring Team
2024-11-07 | 3 | Draft job description. Reference 02_Building an Inclusive Job Description CLI resource. Templates available for program, fundraising/development, community engagement and ED recruitments on the Council Portal. | Alignment | Hiring Team
2024-11-08 | 1 | Establish hiring team. Engage hiring team and existing staff members for feedback on the job description. | Shared Decision-Making, Collaboration, Aligment | Hiring Team
2024-11-09 | 1 | Update position description based hiring team dicussion | Alignment | Hiring Team Lead
2024-11-10 | 1 | Complete CLI Submission Form to submit the role for publishing. | Planning + Coordination | Hiring Team Lead
|  | Posting | Recruitment
2024-11-15 | 5 | Position is posted on Bamboo HR and HQ outlets | Outreach + Candidate Engagement | HQ
2024-11-18 | 3 | Post positions within local and regional outlets. See 04_Hiring Social Media Resources for customizable social media templates. | Outreach + Candidate Engagement | Hiring Team Lead
|  | While position is open, determine interview questions/prompts for first, second and (if applicable) third interviews. See 01_Collaborative Hiring Guide for ideas on how to creatively engage current staff in this stage of the process. | Planning + Coordination, Collaboration, Alignment | Hiring Team
| 14 | Position remains open. Average is about two weeeks, but adjust days in B15 as needed. | Outreach + Candidate Engagement | HQ
2024-12-02 |  | Position Closes |  | HQ
|  | Candidate Review and Engagement | Recruitment/Discernment
Round 1
2024-12-07 | 5 | Hiring team members conduct initial review of candidates | Discernment | Hiring Team
2024-12-12 | 1 | Hiring team selects candidates for first round interviews. | Shared Decision-Making, Collaboration, Aligment | Hiring Team
2024-12-13 | 3 | Invitations to first round interviews are sent. | Planning + Coordination, Outreach + Candidate Engagement | Hiring Lead
2024-12-16 | 7 | First round interviews begin | Outreach + Candidate Engagement | Hiring Team
2024-12-23 |  | First round interviews conclude. | Outreach + Candidate Engagement | Hiring Team
Round 2
2024-12-25 | 2 | Hiring team members conduct review of interview notes. | Discernment | Hiring Team
2024-12-26 | 1 | Hiring team selects candidates for second round interviews. | Shared Decision-Making, Collaboration, Aligment | Hiring Team
2024-12-27 | 1 | Invitations to second round interviews are sent. | Planning + Coordination, Outreach + Candidate Engagement | Hiring Lead
2024-12-30 | 3 | Second round interviews begin. | Outreach + Candidate Engagement | Hiring Team
2025-01-06 | 7 | Second round interviews conclude. | Outreach + Candidate Engagement | Hiring Team
Round 3
2025-01-08 | 2 | Hiring team members conduct review of interview notes. | Discernment | Hiring Team
2025-01-09 | 1 | Hiring team selects candidates for final interviews. | Shared Decision-Making, Collaboration, Aligment | Hiring Team
2025-01-10 | 1 | Final interview invitations are sent. | Planning + Coordination, Outreach + Candidate Engagement | Hiring Lead
2025-01-13 | 3 | Final interviews begin. | Outreach + Candidate Engagement | Hiring Team
2025-01-16 | 3 | Final interviews conclude. | Outreach + Candidate Engagement | Hiring Team
2025-01-17 | 1 | Hiring team meets to discuss and identify chosen candidate. | Shared Decision-Making, Collaboration, Aligment | Hiring Team
2025-01-18 | 1 | Offer is drafted and extended. | Shared Decision-Making, Collaboration, Aligment | Hiring Lead
|  | Offer Acceptance & Onboarding | Recruitment/Discernment
2025-02-01 | 14 | Offer is accepted! Start date is identified.
Formulas:
Date = [Date, row below]-[Time to Complete (In Days), row below]
Date = [Date, row below]-[Time to Complete (In Days)]